## Scenario Brief
EXERCISE SCENARIO: TalentScope AI
Company | TalentScope Solutions — a mid-size HR technology company (300 employees) that provides AI-powered recruitment and talent management tools to enterprise clients across the EU and US.
AI System | TalentScope AI: GenAI recruitment screening — CV parsing/ranking, automated video interview analysis, shortlist generation, culture fit scoring. HIGH-RISK under EU AI Act (Annex III, area 4).
Regulatory Context | EU AI Act (High-Risk), GDPR (Article 22 automated decisions), French AI transparency, German Works Council.
Audit Findings | 8% gender disparity in video confidence scores, candidates not informed of AI use, no risk management system, incomplete training data documentation, no conformity assessment.

## Compliance Matrix
Req ID | Regulatory Requirement | EU AI Act Article | Risk Tier | Technical Control | Status | Evidence Document | Gap Description | Remediation Plan | Owner | Target Date
REQ-001 | Transparency — Inform users that AI is involved in decision-making | Article 13 | High-Risk | User notification system documenting AI use in screening process | "Implemented" Reasoning: TalentScope already has a user notification system for AI use in screening. This is one of the easier requirements — just informing users. The audit didn't flag transparency as a gap. | TR-001-UserNotification.pdf | "None" Reasoning: No gap because the notification system meets Article 13 requirements. Fully implemented means no gap to describe. | "N/A" Reasoning: No remediation needed when status is Implemented. Mark as N/A, not blank — shows you assessed it. | Legal Team | 2024-01-15
REQ-002 | Human Oversight — Enable meaningful human review of AI decisions | Article 14 | High-Risk | Hiring manager review required before any candidate rejection; override capability built in | "Implemented" Reasoning: Hiring manager review is mandatory before rejection — this satisfies Article 14's human oversight requirement. Override capability is built in. | TR-002-HumanOversight.pdf | "None" Reasoning: The workflow already requires human review. This is a strong control — human-in-the-loop before any adverse action. | "N/A" Reasoning: Already compliant. Documenting N/A shows this was evaluated, not skipped. | Operations | 2024-01-20
REQ-003 | Data Governance — Document and ensure quality of training data | Article 10 | High-Risk | Data governance framework with lineage tracking for CV corpus and interview datasets | "Partial" Reasoning: Data lineage tracking EXISTS for CV corpus, but critical gaps remain — no demographic breakdown and interview dataset methodology is undocumented. Article 10 requires comprehensive data documentation. | TR-003-DataGov.pdf | "Training data documentation incomplete — no demographic breakdown of CV corpus; interview dataset collection methodology undocumented" Reasoning: The demographic breakdown is essential because you can't test for bias without knowing your training data demographics. Interview data collection methodology affects data quality claims. | "Complete dataset card with demographic analysis; document interview data collection, consent, and preprocessing steps" Reasoning: Dataset cards are industry standard for documenting training data. Demographic analysis enables the bias testing required by Article 15. Both are concrete, achievable actions. | Data Team | 2024-06-30
REQ-004 | Technical Documentation — Maintain system design records | Article 11 | High-Risk | Technical documentation repository covering system architecture, API specifications, model architecture docs, and data flow diagrams | "Partial" Reasoning: Core CV screening is documented, but video analysis pipeline and culture fit scoring — the most controversial components — are NOT. Article 11 requires complete system documentation. | TR-004-TechDocs.pdf | "Video interview analysis ML pipeline not documented; model versioning not tracked; no documentation of feature engineering for culture fit scoring" Reasoning: Video analysis is where the 8% gender bias was found. Culture fit scoring is inherently subjective. These are the highest-risk components and they're undocumented. | "Document video analysis pipeline end-to-end; implement model versioning; document culture fit scoring methodology" Reasoning: End-to-end pipeline documentation enables audit and review. Model versioning prevents 'which model caused this?' confusion. Culture fit methodology must be defensible. | Engineering | 2024-07-15
REQ-005 | Risk Management — Establish and maintain a risk management system | Article 9 | High-Risk | AI risk management framework aligned with NIST AI RMF; risk register with quarterly review cycle | "Gap" Reasoning: Gap (not Partial) because there is NO risk management system at all — not even a partial one. Ad-hoc risk management doesn't count under Article 9. This is a critical finding. | None | "No formal AI risk management system exists. Risks are managed ad-hoc without systematic identification, assessment, or mitigation tracking" Reasoning: Article 9 requires SYSTEMATIC risk management. 'Ad-hoc' means risks are only addressed when they cause problems, not proactively identified and mitigated. | "Implement NIST AI RMF-aligned risk management framework; create risk register; establish quarterly risk review process; assign risk owners" Reasoning: NIST AI RMF alignment gives a recognized framework. Risk register is the core artifact. Quarterly reviews ensure ongoing management. Risk owners create accountability. | Risk & Compliance | 2024-08-01
REQ-006 | Accuracy & Robustness — Validate performance and prevent errors | Article 15 | High-Risk | Accuracy testing framework with bias detection across protected characteristics; adversarial robustness testing | "Partial" Reasoning: Third-party audit confirmed the gender bias — so some testing exists. But only gender was tested out of many protected characteristics, and no adversarial robustness testing. | TR-006-Accuracy.pdf | "8% gender disparity in video analysis confidence scores confirmed by third-party audit; no testing for race, age, disability, or accent bias; no adversarial robustness testing" Reasoning: 8% gender disparity is the headline finding, but untested characteristics (race, age, disability, accent) could harbor worse biases. No adversarial testing means the system is vulnerable to gaming. | "Expand bias testing to all protected characteristics (race, age, disability, accent); remediate gender disparity to <2%; implement adversarial testing; establish ongoing fairness monitoring" Reasoning: Expanding to all protected characteristics is required by Article 15(2). The <2% threshold is a concrete, measurable target. Ongoing monitoring catches new biases post-deployment. | ML Team | 2024-09-01
REQ-007 | Record Keeping — Maintain logs of system operation | Article 12 | High-Risk | Centralized logging system capturing all screening decisions, candidate interactions, model predictions, and confidence scores with timestamps | "Partial" Reasoning: CV screening is logged, but the video analysis and culture fit scoring — the most sensitive components — are NOT logged at the required granularity. Article 12 requires comprehensive logging. | TR-007-RecordKeeping.pdf | "Logging exists for CV screening but video analysis decisions not logged at granular level; log retention policy not formalized; no audit trail for culture fit score generation" Reasoning: Without granular video analysis logs, you can't audit why specific candidates were scored differently. Culture fit scoring without an audit trail is legally indefensible. | "Extend logging to video analysis pipeline; formalize retention policy (minimum 5 years for EU AI Act); add culture fit scoring audit trail" Reasoning: 5-year retention meets EU AI Act minimum. Extending logging to video and culture fit enables the auditability required for high-risk systems. | Engineering | 2024-07-30
REQ-008 | Conformity Assessment — Complete assessment for high-risk AI | Article 43 | High-Risk | Comprehensive conformity assessment covering all Annex III requirements with internal audit and third-party validation | "Gap" Reasoning: No conformity assessment has EVER been done. This is the critical gateway requirement — without it, the system cannot legally operate as high-risk AI under the EU AI Act. | None | "No conformity assessment has been conducted. This is a critical gap — required before enforcement deadline" Reasoning: Conformity assessment is required BEFORE the enforcement deadline. It's not optional for high-risk systems. This is the most urgent compliance gap. | "Engage accredited third-party for conformity assessment; compile all evidence documentation; conduct internal pre-assessment; schedule formal assessment" Reasoning: Third-party accredited assessor adds credibility. Internal pre-assessment catches issues before formal assessment. This is the longest timeline item. | Compliance Officer | 2024-10-01
REQ-009 | Registration — Register in EU AI database | Article 49 | High-Risk | Registration documentation prepared and submitted to EU AI database for high-risk systems | "Gap" Reasoning: Can't register without completing conformity assessment first. This is a sequential dependency — assessment must come before registration. | None | "Not registered. Registration depends on conformity assessment completion" Reasoning: Registration depends on conformity assessment. The gap isn't negligence — it's a blocked dependency. But preparation can happen in parallel. | "Prepare registration documentation in parallel with conformity assessment; submit within 30 days of assessment completion" Reasoning: Parallel preparation saves time. 30-day submission window after assessment ensures timely registration. Documentation prep can start now. | Legal Team | 2024-10-30
REQ-010 | Bias Prevention — Identify and mitigate discriminatory outcomes | Article 15(2) | High-Risk | Comprehensive fairness testing framework with demographic parity analysis across all protected characteristics; automated bias monitoring in production | "Partial" Reasoning: Gender testing was done (8% disparity found), but that's only 1 of 6+ protected characteristics. Article 15(2) requires comprehensive bias prevention, not single-characteristic testing. | TR-010-BiasPrevention.pdf | "Only gender tested (8% disparity found). Race, age, disability, accent/language, and socioeconomic status not tested. No automated monitoring for bias drift" Reasoning: Testing only gender is like checking only one tire — you need all of them. Race, age, disability, accent, and socioeconomic status could all introduce discriminatory outcomes in hiring. | "Implement comprehensive demographic analysis across 6 protected characteristics; set <2% disparity threshold; build automated bias monitoring with alerting; monthly bias reports" Reasoning: 6 protected characteristics covers major discrimination vectors. <2% threshold is industry best practice. Automated monitoring catches bias drift that point-in-time testing misses. | ML Team + Ethics Board | 2024-09-15
REQ-011 | GDPR Art 22 — Rights related to automated decision-making | GDPR Article 22 | High-Risk | Candidate notification of automated processing; right to human review; right to contest; right to explanation of decision factors | "Gap" Reasoning: Three separate GDPR Art 22 rights are violated — notification, human review, and contestation. Candidates don't even know AI is screening them. This is a major legal exposure. | None | "Candidates not informed AI is used in screening. No mechanism for candidates to request human review or contest automated decisions. No explanation of decision factors provided" Reasoning: Article 22 gives individuals the RIGHT to not be subject to purely automated decisions with significant effects. Hiring decisions clearly qualify. Zero mechanisms exist. | "Build candidate notification system (pre-screening disclosure); implement human review request mechanism; create decision explanation capability; add appeal process with defined SLA" Reasoning: Pre-screening disclosure is the minimum. Human review mechanism satisfies Article 22(3). Appeal process with SLA shows good faith compliance. All three rights must be addressed. | Legal + Product Team | 2024-08-15
REQ-012 | Post-Market Surveillance — Ongoing monitoring after deployment | Article 72 | High-Risk | Production monitoring dashboard tracking accuracy, bias metrics, system availability, and drift detection with automated alerting | "Partial" Reasoning: System availability monitoring is basic IT ops — it doesn't meet Article 72's post-market surveillance requirements for AI. No accuracy monitoring, no bias drift detection. | TR-012-PostMarket.pdf | "Basic system availability monitoring exists. No accuracy monitoring in production, no bias drift detection, no automated alerting for performance degradation" Reasoning: Post-market surveillance for AI means monitoring the AI's decision quality, not just uptime. Bias can drift, accuracy can degrade — uptime monitoring misses all of this. | "Implement production accuracy tracking; add bias drift detection with weekly scans; build automated alerting (threshold-based); establish monthly surveillance reporting" Reasoning: Production accuracy tracking validates ongoing performance. Weekly bias scans catch drift early. Automated alerting prevents silent degradation. Monthly reporting creates accountability. | Operations + ML Team | 2024-08-30
REQ-013 | Serious-Incident Reporting — Notify national competent authority of serious incidents per Article 73 (enforces Aug 2026) | Article 73 | High-Risk | Incident-detection pipeline (sourced from SP6 IR playbook) + 15-day reporting workflow to national competent authority + DPO/Compliance joint sign-off | "Gap" Reasoning: Article 73 enforces from August 2026 for all High-Risk systems. TalentScope has no documented incident-detection-and-reporting pipeline; without it, the company will be non-compliant on day one of enforcement. Severity: high — first regulatory obligation graduates encounter at deployment. | TR-013-IncidentReporting.pdf (planned; does not yet exist) | "Establish 15-day reporting SLA to national competent authority; integrate incident detection from SP6 IR playbook; assign DPO + Compliance lead as joint owners; complete documentation by Q2 2026 ahead of August 2026 enforcement."

## Conformity Evidence
Evidence ID | Req ID | Evidence Type | Document Name | Location | Last Updated | Status | Notes
EV-001 | REQ-001 | Policy Document | User Notification Policy v2.1 | /compliance/policies/notifications/ | 2024-02-28 | "Approved" Reasoning: Evidence fully supports REQ-001 compliance. Policy is current (v2.1), updated for Article 13, and formally approved. This is what complete evidence looks like. | "Updated to include AI system disclosure requirements per Article 13" Reasoning: Highlights that the policy was specifically updated for AI disclosure — shows proactive compliance, not just existing policy repurposed.
EV-002 | REQ-002 | Process Documentation | Human Review Workflow SOP | /compliance/sops/ | 2024-02-20 | "Approved" Reasoning: SOP documents the mandatory review workflow. It's formally approved and operationally active. Strong evidence for human oversight compliance. | "Documents mandatory hiring manager review before candidate rejection" Reasoning: 'Mandatory before rejection' is the key phrase — it's not optional human review, it's required. This distinction matters for Article 14.
EV-003 | REQ-003 | Data Inventory | Training Data Lineage Map | /data/governance/ | 2024-02-25 | "In Progress" Reasoning: Lineage map exists but is incomplete — missing the demographic breakdown that's essential for bias testing. Can't be approved until gaps are filled. | "Tracks CV corpus sources and versions. Missing: demographic breakdown and interview dataset docs" Reasoning: Specifically calls out WHAT's missing so the remediation is targeted, not vague.
EV-004 | REQ-004 | System Architecture | System Design Document v3.0 | /technical/design/ | 2024-02-28 | "Outdated" Reasoning: Document covers old architecture but doesn't reflect current video analysis pipeline or culture fit scoring. Outdated evidence is worse than no evidence — it's misleading. | "Covers core CV screening architecture. Missing: video analysis pipeline, culture fit scoring methodology" Reasoning: 'Missing video analysis pipeline' is critical because that's where the bias was found. Outdated docs for the most problematic component is a red flag.
EV-005 | REQ-005 | Risk Register | None — to be created | N/A | N/A | "Not Started" Reasoning: There's literally nothing to evaluate. The risk register doesn't exist yet. This is the starkest gap — not partial, not outdated, just absent. | "No risk management documentation exists. Risk register and framework to be created as part of remediation" Reasoning: Emphasizes this must be CREATED from scratch. No existing artifact to improve — full build required.
EV-006 | REQ-006 | Bias Assessment | Third-Party Audit Report — Gender Bias | /qa/reports/audit/ | 2024-01-15 | "Reviewed" Reasoning: Audit report exists and has been reviewed, but it reveals a problem (8% disparity). Evidence status is about the document, not the finding. The report is valid evidence even though the finding is bad. | "Confirms 8% gender disparity in video analysis confidence scores. Baseline for remediation tracking" Reasoning: Third-party audit adds credibility. The report serves as baseline — future improvements are measured against this 8% figure.
EV-007 | REQ-007 | System Logs | TalentScope AI Logging Infrastructure | /logs/production/ | 2024-02-28 | "Partial" Reasoning: CV screening logs work fine, but video analysis and culture fit scoring aren't logged properly. Partial logging = partial evidence. | "CV screening logs operational. Video analysis and culture fit scoring not logged at required granularity" Reasoning: 'Required granularity' is key — some logs may exist but not at the detail needed for audit. Granularity matters for high-risk systems.
EV-008 | REQ-008 | Assessment Plan | Conformity Assessment Project Plan | /compliance/assessment/ | 2024-03-01 | "Draft" Reasoning: A project plan exists but the actual assessment hasn't started. Draft status means planning is underway but no evidence of compliance yet. | "Project plan for conformity assessment. Actual assessment not yet started. Third-party assessor shortlisted" Reasoning: Third-party assessor is shortlisted — shows progress. But planning does not equal execution. Draft status reflects the gap between intent and action.
EV-009 | REQ-009 | Registration Prep | EU AI Database Registration Template | /compliance/registration/ | 2024-03-01 | "Not Started" Reasoning: Template is prepared but submission blocked by conformity assessment dependency. Status reflects actual state, not intent. | "Template prepared but not submitted. Awaiting conformity assessment completion" Reasoning: 'Awaiting conformity assessment' explains the blocker. This is a valid sequential dependency, not negligence.
EV-010 | REQ-010 | Test Results | Bias Testing Report — Gender Only | /qa/reports/bias/ | 2024-01-20 | "Insufficient" Reasoning: Evidence exists (gender bias report) but doesn't meet the FULL requirement. Single-characteristic testing is insufficient for Article 15(2). Important distinction from 'Partial.' | "Only covers gender. Race, age, disability, accent not tested. Does not meet Article 15(2) requirements" Reasoning: Lists what's NOT covered to make the gap concrete. Ties the insufficiency to the legal requirement.
EV-011 | REQ-011 | Gap Analysis | GDPR Art 22 Compliance Gap Report | /compliance/gdpr/ | 2024-02-15 | "Action Required" Reasoning: Gap report documenting the problems exists, but no corrective action has been taken. Evidence of the gap exists; evidence of compliance does not. | "Documents all GDPR Art 22 gaps: no candidate notification, no human review mechanism, no appeal process" Reasoning: Lists all three GDPR Art 22 gaps explicitly. 'Action Required' signals urgency — this isn't a monitoring situation, it's a build situation.
EV-012 | REQ-012 | Monitoring Dashboard | System Availability Dashboard | /monitoring/dashboards/ | 2024-02-28 | "Partial" Reasoning: Availability dashboard exists but only covers uptime — not AI performance. For post-market surveillance, this is a small fraction of what's needed. | "Uptime/availability monitoring only. No accuracy, bias drift, or performance degradation tracking" Reasoning: Makes clear this is IT ops monitoring, not AI surveillance. The distinction is crucial for Article 72 compliance.
EV-013 | REQ-013 | Plan Document (placeholder) | Article 73 Incident Reporting Workflow — Draft v0.1 | /compliance/incident-reporting/ | 2026-Q2 (target) | Planned | Pipeline + 15-day SLA defined; integration with SP6 IR playbook in progress; DPO + Compliance owners assigned; ready ahead of August 2026 Article 73 enforcement.

## EU AI Act Risk Tiers
EU AI ACT RISK TIER REFERENCE
Risk Tier | Description | Examples (Annex III) | Key Compliance Requirements
Unacceptable (Article 5) | Prohibited AI practices. | Social scoring, real-time public biometric surveillance, manipulation of vulnerable persons, predictive policing | PROHIBITED — cannot be deployed in the EU.
High-Risk (Article 6, Annex III) | Significant impact on rights/safety. | Employment & recruitment (TalentScope AI), biometric ID, credit scoring, law enforcement, critical infrastructure | Conformity assessment, risk management, data governance, transparency, human oversight, accuracy, documentation, registration, post-market surveillance
Limited Risk (Article 50) | Transparency obligations. | Chatbots, emotion recognition, deepfakes, biometric categorization | Disclose AI usage to users.
Minimal Risk | No specific requirements. | Spam filters, games, basic recommendations, route optimization | Voluntary codes of conduct.
GPAI / Foundation Models (Articles 51–55) | General-Purpose AI models — including those with systemic risk. Added in 2026 EU AI Act refresh. | Foundation-model APIs embedded in customer-facing assistants, chatbots, code copilots, RAG systems. | Transparency to downstream deployers (Art. 53), copyright disclosure, technical documentation; if systemic risk, additional model evaluation + adversarial testing + Art. 55 obligations.